IPC DEVELOPMENT PROGRAM (2006-2008)

FOR THE IPC REVISION WORKING GROUP (IPC/WG)

| Task No. | Task Title | Action | Timeline |
| --- | --- | --- | --- |
| Continuous tasks |
| 1 | Elaboration of classification definitions |  |  |
| 1(a) | Develop a plan for completion of all subclass definitions. | Prepare an updated list of priorities. Prepare a list of prioritized subclasses. | Q2/2006 Q4/2006 |
| 1(b) | Preparation of definitions | Complete definitions for an additional 50 subclasses. | Q4/2008 |
| 2 | Systematic maintenance of the IPC |  |  |
| 2(a) | Develop a plan for maintenance of all subclasses. | Prepare an updated list of priorities. Start pilot projects. | Q2/2006 |
| 2(b) | Treatment of maintenance projects | Complete maintenance of 10 subclasses. | Q4/2007 |
| 3 | Removal of informative references in IPC schemes | Remove informative references from the IPC schemes after completion of corresponding D-projects. | As needed |
| 4 | Removal of references from guidance headings |  |  |
| 4(a) | Develop a plan for removal of references from guidance headings in all subclasses. | Develop plan. | Q2/2006 |
| 4(b) | Removal of references | Remove all references from guidance headings and relocate them in appropriate groups (i.e., limiting type) or in the electronic layer (i.e., informative type). | Q4/2007 |
| 5 | Special Residual Subclasses and Residual Main Groups |  |  |
| 5(a) | Introduction of residual main groups in IPC schemes | Create residual main groups where appropriate. | Q1/2008 |
| 5(b) | Maintenance of special residual subclasses and main groups in IPC schemes | Develop a procedure. Periodical review of all residual subclasses and main groups for emerging technologies or classification problems. | Q2/2006 Continuous |
| Ad hoc tasks |
| 6 | Treating revision projects |  | As needed |
| 6(a) | Treating projects submitted by offices | Collect and evaluate revision projects for the core level, determine their priority and timetable for their elaboration. | As needed |
| 6(b) | Treating projects forwarded from the Advanced Level Subcommittee (ALS) | Treat projects which are forwarded from the (ALS). | As needed |
| 7 | Updating of IPC training examples | Updating existing training examples following a revision project. Introduce a new training example when a new subclass is introduced or an existing one is extensively revised. | As needed |
| 8 | Correction of obvious errors or deficiencies in IPC schemes or definitions | The International Bureau (IB) will evaluate proposals for correcting obvious errors in IPC schemes or definitions and refer to ALS or WG, if appropriate. IB will correct evident clerical errors without further action. | As needed |
| 9 | Evaluate borderlines between the core and advanced levels for problems with hierarchy, ease of use, and correctness of notes, examples or references. | Evaluate and propose improvements to the schemes, notes, examples or references and refer tasks to ALS when appropriate. | As needed |
| 10 | Updating of the Guide and IPC-related documents | Evaluate proposals for new or revised principles or rules for the IPC and propose corresponding changes to the Guide and to IPC-related documents. | Q4/2007 |
| 11 | Quality control of IPC classification | Develop a procedure for investigating significant discrepancies reported between classification symbols applied to members of simple patent families. Propose corrective actions as appropriate. | Q2/2007 Continuous |
| 12 | Preparation of the new edition of the core level of the IPC |  | Q1/2008 |

IPC DEVELOPMENT PROGRAM (2006-2008)

FOR THE ADVANCED LEVEL SUBCOMMITTEE (ALS)

| Task No. | Task Title | Action | Timeline |
| --- | --- | --- | --- |
| Ad hoc tasks |
| 1 | Evaluation of proposed advanced level (AL) revision projects | Evaluate all proposed advanced level revision projects, and other projects forwarded from the WG. Determine the benefit and prioritize these projects according to resources available at the offices performing the reclassification work. | As needed |
| 2 | Treating accepted revision projects | Treat accepted revision projects in accordance with the priorities established in task 1. | As needed |
| 3 | Treating definitions | After completion of an AL revision project, prepare corresponding group definitions and subclass definitions if not available. | As needed |
| 4 | Correction of obvious errors or deficiencies in IPC AL schemes or definitions | The IB will evaluate proposals for correcting obvious errors in IPC schemes or definitions and refer to ALS, if appropriate, for their consideration. IB will correct evident clerical errors without further action. | As needed |
| 5 | Preparation of new versions of the advanced level | Preparation of the new versions of the AL and of corresponding definitions. | As needed |
| 6 | Monitoring reclassification | Ensure that the PCT minimum documentation is reclassified on time after completion of revision projects. | Continuous |
| 7 | Updating of CONOPS | Evaluate whether the procedures described in CONOPS work in a satisfactory way and propose improvements if necessary. | Continuous |

[Annex V follows]