## Capabilities and capacities
New product development capabilities and capacities | [11 empty] | © 2017 KnowWare
Tangible features OR design requirements to realize core benefits sought | Make biofuel | Ease of use sensor and software | Delivery | Biomass for testing | Downstream organisms - adapted for mini-refinery system and/or for different types of biomass. | Feature or requirement 6 | Feature or requirement 7 | Feature or requirement 8 | Feature or requirement 9 | Feature or requirement 10 | Should-cost price
Tasking | License a system and organisms | Find sensors and software and adapt them for our system's remote operations, monitoring, and maintenance | Figure out how to ship it to remote locations with poor roads | Find various sources from all regions so we can test on a range of each target country's biomass. | Better organisms
Labor skills | Production capability and ability to handle organisms | Sensor engineer and software programmer | Logistics manager | Logistics and Procurement | R&D
Knowhow | How to work with the specific organisms that are licensed, and how to optimize the operation of the mini-refinery | Experience with this technology | Logistics and packaging | Nothing special | R&D
Supplies and materials | Vats, conveyors, chippers, mulchers, filters, valves, piping, storage tanks, organisms | Sensors and sofwtare | Crates or containers that can be loaded or contain equipment and be plugged together | Crop or crop waste, other organic waste | Not sure
Equipment and facilities | As needed to do assembly of system and to grow,harvest, and package organisms for shipping, Quality Assurance Lab for organisms and product produced, to ensure standards meet requirements. Could be rented. | Ability to test sensors upon delivery of mini-refinery unit, model for running software | Efficient way to build or acquire packaging | Equipment for preprocessing | Intend to find R&D partner if we pursue this
Technology and IP | License from holder of IP rights in organism(s) and methods, such as Remarkable Biofuels LLC or equivalent. If necessary, license(s) for mini-refinery technology. | License for software. If adapations are made, consider copyright or other data protection for code, perhaps patent for adaptions implemented in a system, if unique enough. | Probably none | Probably none | License from university or research institution holding IP rights. If new organisms are developed, we may generate our own IP.
Working capital | Maybe $1 million USD for prototypes | $500,000 USD | Depending on if containerized, probably under $100,000 USD | Hopefully we can get this free and just have to pick up and deliver to test site(s). Delivery charges should be under $25,000. | Uncertain, may be able to get government grants such as small business grants or grants for biofuels research.
Vendors, contractors and partners needed | Sources for the equipment to be integrated | Sensors and Software | Delivery company | Farms and waste collection facilities | University or research institution
Other factors | Need regulatory expert for any required approvals. Need to prepare manuals for making biofuel. | Manuals will be critical and the best way to handle the telecom piece | Hopefully we can put this out for bid and have someone come up with a solution. | Important to ensure we get a wide range of biomass to run tests on. | If we do a project with a university or research institution, it wold be desirable to have a graduate student involved who could come work for us if it succeeds.

## Action plan framework
| Steps involved and percentage of anticipated progress toward completion | [8 empty] | How it will be accomplished and how you will know it is done
Tangible features OR design requirements | Idea | Screen | Design | Development | Test | Launch | Post-launch | Totals | Stage | Key tasking | Who is responsible for completion | Completion milestone | Budget | Start and end dates
Cutting and mulching waste equipment | 5% | 20% | 20% | 50% | 5% | 0% | 0% | 100% | Idea | Determine feasibility of finding necessary organisms, parts, components, systems |  | Validation that suitable organisms exist and can function in mini-refinery | 5000 | 02/02/2021 - 20/02/2021
Brewing vats and capture tanks | 5% | 20% | 35% | 25% | 15% | 0% | 0% | 100% | Screen | Establish market, technical and financial viability | Market work - Market Research Expert; Technical viability - Engineering Expert and Legal Consultant; Financial - Finance and Budgeting Expert | Establish Competitive Advantage and Freedom to Operate; Establish that market entry is feasible for product concept; attain technology readiness level (TRL) 2 | 25000 | 01/03/2021-25/05/2021
Cleanable filters | 5% | 20% | 20% | 40% | 15% | 0% | 0% | 100% | Design | Estalish a Business Model Canvas; fix technical approach, license organisms, and establish proof of concept; complete design project consistent with model | Business Model Canvas - Team Leader; Technical approach and design - Engineering and Technical Expert and Design Consultant; IP and supplier/vendor qualification and contracting - Logistics Expert with Legal Consultant | Business Canvas Model approved; licenses for organisms obtained; attain TRL 3; design approved; vendors/suppliers qualified and contracts in place | 100000 | 01/07/2021 - 30/11/2021
Piping and valves | 5% | 20% | 35% | 25% | 15% | 0% | 0% | 100% | Development | Develop benchtop prototype and operational prototype; raise rest of necessary funding | Engineering and Technical Expert with Production Engineering Consultant | Attain TRLs 4, 5, 6, and 7 | $170,000 through TRL 4, Additional $1.3M as raised | 01/12/2022 - 28/10/2022
Conveyors | 5% | 20% | 20% | 40% | 15% | 0% | 0% | 100% | Test | All certifications and regulatory complaince, completion of Beta testing | Engineering and Technical Expert and Logistics Expert with Legal Consultant | Attain TRL 8 and 9; receive all necessary certifications and registrations | 500000 | 01/11/2022 - 28/03/2023
Fungi/organisms for biodiesel, ethanol, and hydrogen | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100% | Launch | Prepare manuals and train Market and Sales Personnel, Sales Reps, Installers, and Maintenace Repair Personnel; implement marketing campaign; establish corporate and retail sales channels | Training - Team Leader with Training Consultant; Marketing and Sales - Business Development Expert and Sales and Marketing Department Manager | Personel trained for launch and support; Marketing campaign implemented; sales channels established, initial revenue targets hit | 200000 | 01/04/2023 - 28/08/2023
Controls for on-site and remote operations, monitoring, and preventative maintenance | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100% | Post-launch | Revamp manuals and training materials as needed; enhance on-line training and support with better software and platforms if available and affordable; develop list of desirable improvements/enhancements/adds | Product Line Manager. Team Now Acts as In-House Consultants | Removal of product from sales plans | To be provided by Product Line Manager as needed | 15/01/2024 - 30/12/-2043
Sensors for on-site and remote operations, monitoring, and preventative maintenance | 5% | 20% | 25% | 25% | 20% | 0% | 5% | 100%
Software for on-site and remote sensors and controls for operations, monitoring, and preventative maintenance | 5% | 25% | 25% | 25% | 20% | 0% | 0% | 100%
Modularize for transport | 5% | 15% | 35% | 30% | 10% | 0% | 5% | 100%
Should-cost price | 5% | 15% | 40% | 20% | 10% | 5% | 5% | 100%
Time Line

## Notes and references
Notes:
Timing and budgets based on interviews with members of the team with certified NPD Professionals with experience with related products. The certification is from the Product Development and Management Association. Tasking developed by team and checked with PDMA members during interviews to ensure they are reasonable and complete.
References: